HWC MANAGEMENT ACTION PLAN 2013

| WHEN | ACTIVITIES (WHAT) | WHO | HOW (Target Group) | BUDGET | BUDGET SOURCE |
| --- | --- | --- | --- | --- | --- |
| 21st Jan 2013 29th Jan 2013 January 2013 – completed with certificate in February 2013 March, 2013 23rd Feb, 2013 April 4th April, 2013 | 2013 Planning meeting at Kohea & membership review. Presentation of 2013 Action Plan – Venue Kohea IPA Registration Cross-cutting Issue's: (Life Clock, LPA, CRC, Human Rights, Drug and Alchohol) Rice Mill Shed CPAD – Evaluatiion Extraordinary General Meeting to plan for Mini Show in June. | HWC Executives HWC General meeting Dorcas Gano – President + HWC Executives WIEA EEA HWC Executives + 6 Districts DCDO's HWC Executives + Show Committee Meeting – Tanamalo Tsuhana | Executives and EEA, WIEA, CDI Leaders General membership across Hako plus chiefs to plan for adoption ceremony of CAPS Commander Hako Day High School + Upper Primary students x 6 Primary Schools. | Donated catering from Kohea Pot Luck (Everyone cook ) K700.00 K10,000.00 K10,000.00 | HWC members All members to contribute food and meet own transport to travel to venue of meeting. Donation from Australia c/- M Havini as HWC Fundraising Law & Justice a)Follow up Letter to Member Beani b) HWC members Basket for Moni to invited people. Bring food together, everyone to contribute |
| 7th May 2013 4th June, 2013 13th June 2013 June 21st & 22nd 11th July, 2013 | Quarterly Meetings Extraordinary General Meeting to plan for Mini Show in June CPAD Evaluation Workshop AGM – Mini Show World Population Day: (Family Planning, Safe Motherhood, Maternal Health) | HWC Executive Board Meeting HWC Executives + Show Committee Meeting – Tanamalo Tsuhana HWC, BWF, Hako Media Unit, UNDP, UNW, Hon Minister Dare & EO Com Dev, Family Support Centre, District Officers Nth B’villle HWC Elected executives + Show Committee to be appointed. Church Groups | 6 Districts of North Bougainville – CPAD Teams representing NGO (BWF, Youth, Churches,) and GO (Dist Office, COE, DCDO) | US$500 (PGK 995,21) K10,0000 K10, 000 | Tranche 3 of UNDP CPAD Project from Fiji Office Care PNG/PSI/BHCP/HIV Aids Hon. Lauta Atoi |
| 6th Aug 2013 | Quarterly Meetings | HWC Executive Board Meeting Youth/Women |  | K30,000.00 |  |
| 15 – 16 Oct., 2013 5th Nov 2013 10 Dec., 2013 | 3 days Hako Expo – Hako community Quarterly Meetings Human Rights/Hygine/Sanitation Committee | World Rural Women's Day/World Food Day & World Day to alleviate poverty. HWC Executive Board Meeting Training |  | K10,000.00 K13,000.00 | BWF/AusAid/DPI law & Justice/UNICEF |